## Slide 1: Game of Research Methods
Project Kick off Meeting
Feb 5 2020

## Slide 2: Programme
Project summary
Problem
Goals
Work packages, Deliverables and Deadlines
Tasks
Team
Partners
Communication
First tasks

## Slide 3: Project Summary
Start 01.01.2020 (contract signed 16.01.2020)
End 31.12.2020
Duration 1 y
Budget 71 429 €

## Slide 4: Problem
Learning RM is boring
Low quality of game studies
RM teaching is mostly based on traditional instructional methods
Not enough research topics and supervisors

## Slide 5: Project Goal
Create a learning (adventure?) game that increases the motivation and competences with regards of research methods.

## Slide 6: Sub-Goals
Database of research methods
Mini-games about research methods
AI based recommendation system (NPC’s)
Database of research topics and supervisors
Learning analytics of players preferences and typical mistakes
Outcome of the game is research plan.

## Slide 7: Work Packages (Deliverables) and Deadlines
WP1 Needs analysis [Jan 31]
WP2 Research process model [Feb 29]
WP3 Database of research topics and supervisors [Apr 30]
WP4 Game conceptual design [May 31]
WP6 Game development [Oct 31]
WP7 Piloting [Dec 31]
WP8 Project management

## Slide 8: Project Tasks
WP1 Needs
  Collecting the stakeholders needs (universities, students, industry, …)
WP2 Model
  Existing reseach models
  General structure of the research process
  Details for selection
WP3 Database
  Collecting supervisors (50, including 25 from industry)
  Collecting research topics (100)
  Creating the database
  Creating a web page
WP4 Design
  Game concept
  Minigames
WP5 Development
  Developing game modules and mini games in iteration
  Alpha testing
WP6 Piloting
  Beta testing (50 students)
  Feedback from stakeholders (> 75% satisfactory)
WP7 Management
  Communication platform
  Documentation

## Slide 9: Project Gantt Chart

## Slide 10: Project Budget
Item | Cost
Labour | 47 620
Traveling | 1 393
Hard- and software, materials | 4 980
Subcontracting | 0
Seminars and meetings | 3 150
Overhead cost | 14 286
Total | 71 429

## Slide 11: Team
Ralph Söthe-Garnier - DES
David Robert Upshall - DES
Peadar Callaghan - DES
Roman Gorislavski - DEV
Ahmed Mohamed Said Anwar Elshenawy - DEV
Osman Sinan Emiroğlu - DEV
Elena Gorshkova - ART
Iryna Selina - ART
Asian Hõ - ANI
Oluwafiyikewa Aigbovbioise Alawode - SND
Martin Sillaots - PM
Mikhail Fiadotau - PA
Tobias Ley - EXP
Triinu Jesmin - EXP
Kai Pata - EXP

## Slide 12: External Partners
IGDA Estonia - Marianna Krjakvina
Mainor - Marge Robam
EBS - Ülle Pihlak
UT - Madis Vasser
TalTech GameLab - Ingvar Lond
Jyväskylä - Tanja Välisalo
Utrecht - Remco Veltkamp

## Slide 13: Communication
Weekly meetings - 1h (preferred day and time: Th 15:00 - 16:00)
  LIFE RM game project meetings on Th 17:00 - 19:00
Workspace - GitHub ?
Chat - Slack ?
…

## Slide 14: First tasks
Ideas for the general game concepts
  What genre: adventure, RPG, strategy?
  What theme and stile?
  What story?
Ideas for mini games and challenges
  Ideas from the course of Research Methods
What role you would like to take?
Estimate the contribution you can make
  Expected workload 25% (10 h per week)
What are your needs as a user (student) for this game?
  Small empirical study